## Bug Reports
Bug ID | Module / Screen | Summary | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Test Environment | Status
LS2-01 | Main Screen / About Author | UI Lock: Navigation trap inside 'About Author' menu (both UI 'Back' button and Android system gesture fail) | Critical | High | 1. Launch the game and navigate to the Main Menu. 2. Tap the 'About Author' button to open the info overlay. 3. Attempt to return to the Main Menu using the in-game 'Back' button. 4. Attempt to return using the Android system back button/gesture. | The 'About Author' overlay dismisses cleanly and returns the user to the Main Menu upon either input. | Both UI 'Back' button and Android system gesture inputs are completely ignored; user is trapped on the screen and forced to kill the app process. | Samsung Galaxy S22 (Android 14) | Open
LS2-02 | Main Screen / Start Game | Level Launch Blocker: Selected 3D level fails to load upon tapping level card | Blocker | Highest | 1. Launch the game and tap 'Start Game' from the Main Menu. 2. In the level selection carousel, highlight any unlocked stage (e.g., Level 1). 3. Tap on the level card or the 'Play' trigger button. | Loading sequence initiates and the 3D level scene environment renders successfully. | Tap registers visually but scene transition never triggers; application stays static on the level selection screen. | Google Pixel 7 (Android 14) | Open
LS2-03 | Start Game / Top Bar | Settings Modal Failure: Tapping gear icon in top-right header does not open game settings | Major | High | 1. Navigate to the 'Start Game' section from the Main Menu. 2. Locate the settings (gear) icon in the top-right corner of the header. 3. Tap the gear icon. | Settings modal opens displaying audio volume sliders, graphics quality presets, and control sensitivity options. | Tap event is ignored; settings modal does not appear, and the gear icon remains static. | Xiaomi Redmi Note 12 (Android 13) | Open
LS2-04 | Start Game / Top Bar | Header Touch Unresponsive: Social icon cluster (Mail and Profile Avatar) in top-right header drops touch events | Minor | Low | 1. Navigate to 'Start Game' screen from Main Menu. 2. Tap the mail (envelope) icon in the top-right header and observe UI response. 3. Tap the adjacent circular player avatar icon in the top-right header and observe UI response. | Each icon highlights on touch and launches its respective dialog (Mailbox announcements overlay and Player Profile statistics card). | Touch events are completely dropped across the social icon container; neither icon animates, highlights, or opens any overlay. | Samsung Galaxy A54 (Android 13) | Open
LS2-05 | Start Game / Navigation | UI Freeze: Screen freezes completely upon tapping 'Exit' button | Critical | High | 1. Navigate to the 'Start Game' section from the Main Menu. 2. Tap the 'Exit' / 'Return' button located at the bottom-left corner. | Lobby scene unloads cleanly and user is returned to the Main Menu with smooth transition. | Screen freezes instantly with total touch unresponsiveness; application hangs indefinitely and requires process restart. | Samsung Galaxy S22 (Android 14) | Open

## Summary & Analytics
🎮 LAST SIGNAL 2 — QA Bug Report Portfolio Audit
Commercial Verification ¦ PixelCraft Studio ¦ 3D Indie Title (Android Active Testing Phase) ¦ Dmitry Kravchenko
TOTAL DEFECTS | BLOCKER | CRITICAL | MAJOR | MINOR | STATUS: OPEN
5 | 1 | 2 | 1 | 1 | 5
Defect Severity Classification
Severity Level | Defect Count | % of Total | Engineering Action
Blocker | 1 | 20% | Immediate Level Loading & Core Loop Hotfix
Critical | 2 | 40% | Navigation & UI Trap Resolution (About Author / Exit)
Major | 1 | 20% | Settings Modal & Preferences Configuration
Minor | 1 | 20% | Header Icons Touch Event Routing (Mail / Avatar)
Total | 5 | 100% | 100.0% Production Audit Scope